## Sheet1
ENSYFI - Kalaimagal updates
S.No. | Task | Status | Dev Time | Testing Time
1 | Update the changes made in live to kvmhs also without affecting their existing data |  | 14 hrs | 7 hrs | Completed - Need to test
2 | Change the name to EMIS |  | 10 mins |  | Completed
3 | Option to upload TC soft copy |  | 20 mins | 30 mins | Completed
4 | Web cam access to take picture of student during registration in web app |  | 1 hr | 1 hr | Need to discuss with nandha
5 | Send login id and school id to new students through sms | yes working needed to enable | 20 mins |  | Completed
6 | Also send login id and school id along with app url to all the existing student's parents through sms |  | 10 mins | 30 mins | Completed
7 | Enable tab option in web app |  | 30 mins | 30 mins | Completed
8 | Web view is not looking good in mobile app |  | 4 hrs |  | Designing Work
9 | Timetable is not proper in web - check and give solution |  | 5 mins |  | Designing Work
10 | In KVMHS website, CMS, Scroll. Change the color to improve visibility | Color change in newsfeed in kalaimagal website |  |  | Designing Work
11 | While adding Image size greater 1mb, show alert |  | 30 mins | 30 mins | Completed